NEWIC Strategic Plan Dashboard (January 2017)

Vision & Mission:  The vision of NEWIC is to eliminate vaccine preventable diseases through 100% immunization rate and to establish a network of providers and consumers who share the common interest of increasing immunization levels in our communities.

| SCORE KEY |
| --- |
| 0 | Not Started |
| 1 | In Progress |
| 2 | Completed |

Goal 1:  Advocate the use of policies that facilitate improving immunization levels.

| Action Strategy | Activity (Input/Output) | Accountability | Projected Due Date | Status | Score |
| --- | --- | --- | --- | --- | --- |
|  |  |  | `15 | `16 | `17 |  |  |
| 1.1 Promote current state & national recommendations | Maintain website-feature immunization providers Maintain Facebook page-incorporate hot topics Recognize IZ champion on website/FB/press release | Website Redesign with new url Ongoing Ongoing 3rd year | X | X |  | Web/Media/PR committee needs to meet with Catherine to learn website posting & make any recommended changes to layout/content | 2 |
|  | Update website at least monthly | Ongoing | X | X |  | Agendas added NEWIC meeting events created quarterly Add symposium or other events prn | 2 |
|  | Increase public following on social media (Facebook) each year by at least 40%. Use informatics on Facebook & Twitter to analyze engagement | 100 likes currently Website/Media Comm. | X | X |  | Increased in past year Event posting & sharing will be boosted with HPV Grant Funds | 2 |
| 1.2 Support professional education to assist providers in following pediatric and adult standards for immunization practice. | Education Outreach (ie.webinars, symposium) | Website/Media Committee HPV Grant Committee (LHD & reps) | X | X |  | Website redesign Order refrigerator magnets with new web address Partner with NAO/AHEC project to increase HPV immunization rates in NE WI Val Davis is coordinating grant activities | 1 |
|  | Symposium | Symposium Committee |  | X |  | Date & venue selected Speakers engaged Draft of Save the Date | 2 |
| 1.3 Coordinate public & private efforts in our region with those at the state and national level. | Educate policy makers on IZ issues* | General Coalition Members | X | X | X | Report from WCIP and Regional Immunization Program Advisor | 2 |
|  | Share immunization benchmark data from NE Region on website/Facebook | New Initiative (Annually) | X | X | X | Share data from WDHS Immunization Program on website & Facebook Links to state data | 1 |
|  | Share IZ impact outcomes (ie. Pertussis incidence vs. immunization rates on website/Facebook | Ongoing | X | X | X | Shared doctor group making statement about vaccine exemptions in WI Added Pertussis Info Graphic to FB | 1 |
|  | Add link for HCW flu vaccination rates in WI to website | Web/Media/PR Committee | X |  |  | Need to find and post | 0 |
| 1.4 Maintain & recruit membership | Outreach to pharmacists, IZ provider groups (Pharmacy Society of WI, Fox Valley Healthcare Professionals, parish nurses) | LHD reps/ongoing |  |  |  | Continue to send out agenda and minutes for each meeting to all contact groups | 1 |
|  | Utilize technology for regular coalition meetings or work groups whenever possible. | Chair | X | X |  | Research availability at meeting sites Teleconference line being used for Executive Committee meetings | 2 |
|  | Survey Monkey for meeting times every even year | Chair | N/A | X | N/A | Due in 2016 Done in October 2016 | 2 |

| Action Strategy | Activity (Input/Output) | Accountability | Projected Due Date | Status | Score |
| --- | --- | --- | --- | --- | --- |
|  |  |  | `15 | `16 | `17 |  |  |
| 2.1 Develop “pro vaccine” messages targeted to specific life course stages | Revise website: Add accessible resources to website with recommended materials for community organizations/agencies | Media/PR Committee | X | X | X | Web/Media/PR committee needs to meet with Catherine to learn website posting & make any recommended changes to layout/content | 2 |
|  | Add accessible resources to website with recommended materials for general public | Media/PR Committee | X | X | X | Agendas added NEWIC meeting events created quarterly Add symposium or other events prn | 2 |
|  | Finalize and approve Media Plan | Kim Wildes Media/PR Committee | X |  |  | Social Media Policy is developed | 2 |
|  | Community-wide media campaign for HPV Grant - Movie Trailer - Billboards - Engage community partners - Provider Education Activities - Cable TV | Community Partners Committee/coalition members | X | X |  | Billboard in DePere Sept. 2014 Contract w/ Screen Vision to use CDC video & add NEWIC logo Contracted with Lamar Advertising for billboards on Hwy 41 corridor Reach out to regional chapter of American Cancer Society Contacted by NAO/AHEC about partnership to work with providers over next 5 years CDC Grant extended another year through 10/31/17 | 1 |
|  | Provide speakers for community agencies working with target populations | Coalition members | X | X | X | Support local efforts by providing honorariums for speakers with board approval | 1 |

GOAL 2: Educate the consumer with clear, consistent messages about the importance of immunizations.

GOAL 3: Identify barriers to immunization and strategize measures to eliminate them

| Action Strategy | Activity (Input/Output) | Accountability | Projected Due Date | Status | Score |
| --- | --- | --- | --- | --- | --- |
|  |  |  | `15 | `16 | `17 |  |  |
| 3.1 Disseminate tools and resources to assist providers & staff to improve communication skills with consumers about vaccinations | Develop "Master Policy" Templates* (ie. Links for AAP Declination Form, WI Immunization Program Policies, Immunization Philosophy Statement on website and facebook) | Media/PR Committee | X | X | X | Web/Media/PR committee needs to meet with Catherine to learn website posting & make any recommended changes to layout/content Committee Met Updates to content need to be made to website Billing for hosting and domain name will be set up with debit card for 2017 | 1 |
|  | Provide speakers for professional education seminars | Coalition members | X | X | X | Did presentation at CMA conference in 2014 Lunch & Learn on HPV for TCP in August of 2016 | 1 |